## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As an admin I need to be able to log into BOOKEROO, so that I can access the admin panel | David Aziz | High | 5 | TO DO | wireframe,frontend, backend, database
2 | As an admin I need to able to review the connectivity of BOOKEROO, so that I can ensure all users have access to the system | David Aziz | Medium | 13 | TO DO | frontend, backend, database
3 | As an unregistered customer I need to signup to BOOKEROO, so that I can gain access to standard account specific features | David Aziz | Medium | 13 | TO DO | wireframe,frontend, backend, database
4 | As a registered customer I need to login to BOOKEROO, so that I can access all the customer related features such as puchasing booking | David Aziz | Medium | 13 | TO DO | wireframe,frontend, backend
5 | As an unregistered publisher/shop owner I need to signup to BOOKEROO, so that I can have access to the related features such as putting up books for sale | David Aziz | Medium | 13 | TO DO | wireframes,frontend, backend, database
6 | As a registered publisher/shop owner I need to be able to log into BOOKEROO, so that I can access the features of a publisher/shop owner | David Aziz | Medium | 5 | TO DO | wireframes,frontend, backend, database
7 | As an admin I need to be able to approve/deny registration of publishers/shop owners, so that I have control over the which parties have access to the site | David Aziz | Medium | 8 | TO DO | frontend, backend, database
8 | As a publisher/shop owner I need to be able to add books, so that I may present them to customers for purchase | David Aziz | Medium | 8 | TO DO | wireframe,frontend, backend, database
9 | As a publisher/shop owner I need to be able to remove books that are no longer for sale, so that customers do not attempt to purchase them | David Aziz | Medium | 8 | TO DO | frontend, backend, database
10 | As a customer i need to be able to search for books by name, author, catergory or ISBN, so that I can find a book I would like to purchase | David Aziz | Medium | 8 | TO DO | wireframe,frontend, backend, database
11 | As a customer I need to able to view all books with their cover images, so that I can easily recognize each book | David Aziz | Medium | 5 | TO DO | frontend, backend
12 | As an admin I need to be able to block users of all types, so that they may no longer use their accounts on BOOKEROO | David Aziz | Medium | 5 | TO DO | frontend, backend, database
13 | As an admin I need to be able to add new books so that customers may view and purchase them | David Aziz | Low | 8 | TO DO | frontend, backend, database
14 | As an admin I need to be able to edit new books so that customers see upto date information about these books | David Aziz | Medium | 8 | TO DO | frontend, backend, database
15 | As an admin, I need to be able to remove books that have violated BOOKERO's book publishing/selling guidelines. | David Aziz | Medium | 13 | TO DO | frontend, backend, database
16 | As a publisher/shop owner I need to be able to edit information about the book such as cover pages, so that I may present the most upto date information to customers | David Aziz | Medium | 5 | TO DO | frontend, backend, database
17 | As a publisher/shop owner I need to able to edit my paypal information, so that I may receive payments to a new account | David Aziz | Medium | 8 | TO DO
18 | As a customer i need to be able place an order for a book I wish to purchase using paypal as a payment method, so that I can obtain the book | David Aziz | Medium | 8 | TO DO | wireframe,frontend, backend, api
19 | As a customer I need to be able to cancel an order until 2 hours after the item has been ordered, so that I can change my mind or remove a book I ordered accidentally | David Aziz | Medium | 8 | TO DO | frontend, backend
20 | As a customer I need to able to view my orders status so that I can know what I have not recieved yet. | David Aziz | High | 8 | TO DO | frontend, backend, database
21 | As a customer I need to be able to send a refund request for a book I ordered, so that I can get my money back if the product wasn't what I expected | David Aziz | Medium | 8 | TO DO | frontend, backend
22 | As a publisher/shop owner I need to be able to mark books that are currently out of stock, so that customers do not attempt to purchase them | David Aziz | Medium | 5 | TO DO | frontend, backend, database
23 | As an admin I need to able to review a summary of all past and current transactions sorted by date, so that I can review the activity of the site | David Aziz | Medium | 8 | TO DO | frontend, backend, database
24 | As a publisher/shop owner I need to be able to see a history of all transactions that have occured through BOOKEROO, so that I can keep track of my sales | David Aziz | Medium | 13 | TO DO | wireframe,frontend, backend, database
25 | As a customer I need to be able to view my tansactions history so that I can know what I have bought exactly. | David Aziz | Medium | 5 | TO DO | frontend, backend, database
26 | As an admin I need to be able to generate a report about a day, month or year transactions, so that I can follow the activeness of the application in the form a csv file | David Aziz | Medium | 5 | TO DO | wireframes,frontend, backend, database
27 | As a customer i need to be able to review a book that I have purchased, so that I can share my thoughts and opinions on that book | David Aziz | Medium | 5 | TO DO | wireframe,frontend, backend
28 | As a customer, I need to be able to perform create/update/delete operations with my reviews that I posted. | David Aziz | Medium | 5 | TO DO | frontend, backend

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | As an admin I need to be able to log into BOOKEROO, so that I can access the admin panel | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | As a publisher/shop owner I need to be able to see a history of all transactions that have occured through BOOKEROO, so that I can keep track of my sales | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a publisher/shop owner I need to able to edit my paypal information, so that I may receive payments to a new account | #N/A | #N/A | #N/A | #N/A | #N/A
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | As an admin I need to able to review a summary of all past and current transactions sorted by date, so that I can review the activity of the site | #N/A | #N/A | #N/A | #N/A | #N/A
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | As a customer i need to be able to search for books by name, author, catergory or ISBN, so that I can find a book I would like to purchase | #N/A | #N/A | #N/A | #N/A | #N/A
15 | As a customer i need to be able to review a book that I have purchased, so that I can share my thoughts and opinions on that book | #N/A | #N/A | #N/A | #N/A | #N/A
16 | As a customer i need to be able place an order for a book I wish to purchase using paypal as a payment method, so that I can obtain the book | #N/A | #N/A | #N/A | #N/A | #N/A
17 | As a customer I need to be able to cancel an order until 2 hours after the item has been ordered, so that I can change my mind or remove a book I ordered accidentally | #N/A | #N/A | #N/A | #N/A | #N/A
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | As a customer I need to able to view my orders status so that I can know what I have not recieved yet. | #N/A | #N/A | #N/A | #N/A | #N/A
20 | As a customer I need to be able to view my tansactions history so that I can know what I have bought exactly. | #N/A | #N/A | #N/A | #N/A | #N/A
21 | As a customer I need to able to view all books with their cover images, so that I can easily recognize each book | #N/A | #N/A | #N/A | #N/A | #N/A
22 | As a customer, I need to be able to perform create/update/delete operations with my reviews that I posted. | #N/A | #N/A | #N/A | #N/A | #N/A
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!